## Sheet1
Functionalitate | Task | Prioritate Functie | Estimare Task | Status | Stoica Alexandru | Stoenica Robert | Sirbu Claudiu
Login | interfata grafica | 0 | 4h | Neinceput |  | x
Login | logica autentificare | 0 | 5h | Neinceput |  | x
Authetification error | all functionality | 0 | 3h | Neinceput |  | x
Password retrieval | interfata grafica | 0 | 3h | Neinceput |  | x
Password retrieval | email si redirect | 0 | 5h | Neinceput |  | x
Change password | all functionality | 0 | 4h | Neinceput |  | x
Submitting projects | interfata grafica | 1 | 4h | Neinceput | x
Submitting projects | model baza de date | 1 | 2h | Neinceput | x
Submitting projects | functionalitate logica | 1 | 6h | Neinceput | x
Add comments on project | all functionality | 2 | 6h | Neinceput | x
Grade students | all functionality | 1 | 5h | Neinceput |  | x
Leave feedback | all functionality | 2 | 4h | Neinceput |  | x
View submitted projects | interfata grafica | 2 | 3h | Neinceput | x
View submitted projects | model baza de date | 2 | 2h | Neinceput | x
View submitted projects | functionalitate logica | 2 | 4h | Neinceput | x
Set deadline | interfata grafica | 1 | 3h | Neinceput |  |  | x
Set deadline | functionalitate logica | 1 | 4h | Neinceput |  |  | x
Set deadline | consecinte trecere deadline | 1 | 4h | Neinceput |  |  | x
View courses | interfata grafica | 1 | 5h | Neinceput |  |  | x
View courses | functionalitate logica | 1 | 4h | Neinceput |  |  | x
Grade viewing | interfata grafica | 3 | 5h | Neinceput |  |  | x
Grade viewing | functionalitate logica | 3 | 4h | Neinceput |  |  | x
Grade filtering | all functionality | 3 | 5h | Neinceput |  |  | x
Generate PDF report | all functionality | 3 | 6h | Neinceput | x
Download reports | all functionality | 3 | 3h | Neinceput | x
Report generation error | all functionality | 3 | 3h | Neinceput |  |  | x
Profile editing | interfata grafica | 1 | 4h | Neinceput |  | x
Profile editing | functionalitate logica | 1 | 5h | Neinceput |  | x
Registering to optional courses | interfata grafica | 4 | 3h | Neinceput |  |  | x
Registering to optional courses | functionalitate logica | 4 | 4h | Neinceput |  |  | x
Download project | all functionality | 2 | 5h | Neinceput |  |  | x
Assign users to projects | all functionality | 0 | 6h | Neinceput | x
Manage courses | interfata grafica | 1 | 4h | Neinceput | x
Manage courses | logica creere cursuri | 1 | 5h | Neinceput | x
Manage courses | logica editare cursuri | 1 | 4h | Neinceput | x
Manage courses | logica stergere/curatare cursuri | 1 | 4h | Neinceput | x
Manage users | interfata grafica | 0 | 4h | Neinceput |  | x
Manage users | logica creere useri | 0 | 5h | Neinceput |  | x
Manage users | logica editare useri | 0 | 4h | Neinceput |  | x
Manage users | logica stergere useri | 0 | 4h | Neinceput |  | x